## Scenario Summary
Scenario Summary
|  | Current Values: | Opt E | Pess E | ML
|  |  | Created by Microsoft Office User on 10/4/2022 Modified by Microsoft Office User on 10/4/2022 | Created by Microsoft Office User on 10/4/2022 | Created by Microsoft Office User on 10/4/2022
Changing Cells:
| $C$7 | 95 | 90 | 100 | 95
| $D$7 | 65 | 60 | 70 | 65
| $E$7 | 35 | 30 | 40 | 35
Result Cells:
| $B$15 | 123 | 118 | 128 | 123
| $C$15 | 165.3611 | 165.3611 | 165.3611 | 165.3611
Notes: Current Values column represents values of changing cells at
time Scenario Summary Report was created. Changing cells for each
scenario are highlighted in gray.

## Sheet1
| PERT 3 Time Estimates |  |  |  | E(V) | Var | Completion
Activity | Pessimistic | ML | Optimistic | Predecessor | (to+4ML+P/6) | ((tp-To)/6)^2 | 0
A | 20 | 10 | 5 | - | 10.8333 | 6.25 | 10.8333
B | 12 | 7 | 5 | - | 7.5 | 1.3611 | 7.5
C | 12 | 10 | 8 | A | 10 | 0.44444 | 20.8333
D | 45 | 25 | 12 | C | 26.1667 | 30.25 | 47
E | 95 | 65 | 35 | D | 65 | 100 | 112
F | 14 | 10 | 7 | D | 10.1667 | 1.3611 | 57.1667
G | 45 | 30 | 15 | C | 30 | 25 | 50.8333
H | 12 | 10 | 8 | E,F,G | 10 | 0.44444 | 122
I | 6 | 4 | 3 | B | 4.1667 | 0.25 | 11.6667
J | 1 | 1 | 1 | H,I | 1 | 0 | 123
mean | Var |  | LL | UP
123 | 165.3611 |  | 84.4222 | 161.5778